## E5SP TOP (Tape) (Jan)
Week / Date | Day Shift | [5 empty] | Night Shift | [5 empty] | Daily Total
| Workers |  | Production Qty |  |  | Output per Person | Workers |  | Production Qty |  |  | Output per Person | Workers |  | Production Qty |  |  | Output per Person
| Net Workers | Assigned | Plan | Actual | Achievement Rate |  | Net Workers | Assigned | Plan | Actual | Achievement Rate |  | Net Workers | Assigned | Plan | Actual | Achievement Rate
2026-01-01
2026-01-02 | 3 | 3 | 600 | 585 | 97.5% | 195 | 3 | 3 | 600 | 645 | 107.5% | 215 | 6 | 6 | 1200 | 1230 | 102.5% | 205
2026-01-03
2026-01-04
2026-01-05 | 3 | 3 | 600 | 570 | 95% | 190 | 3 | 3 | 600 | 645 | 107.5% | 215 | 6 | 6 | 1200 | 1215 | 101.2% | 202.5
2026-01-06 | 3 | 3 | 600 | 585 | 97.5% | 195 | 3 | 3 | 600 | 645 | 107.5% | 215 | 6 | 6 | 1200 | 1230 | 102.5% | 205
2026-01-07 | 3 | 3 | 600 | 510 | 85% | 170 | 3 | 3 | 600 | 600 | 100% | 200 | 6 | 6 | 1200 | 1110 | 92.5% | 185
2026-01-08 | 3 | 3 | 600 | 600 | 100% | 200 | 3 | 3 | 600 | 630 | 105% | 210 | 6 | 6 | 1200 | 1230 | 102.5% | 205
2026-01-09 | 3 | 3 | 600 | 673 | 112.2% | 224.3333 | 3 | 3 | 600 | 450 | 75% | 150 | 6 | 6 | 1200 | 1123 | 93.58% | 187.1667
2026-01-10
2026-01-11
Week 1 | 3 | 3 | 3600 | 3523 | 97.86% | 195.7222 | 3 | 3 | 3600 | 3615 | 100.4% | 200.8333 | 6 | 6 | 7200 | 7138 | 99.14% | 198.2778
2026-01-12 | 3 | 3 | 600 | 570 | 95% | 190 | 3 | 3 | 600 | 435 | 72.5% | 145 | 6 | 6 | 1200 | 1005 | 83.75% | 167.5
2026-01-13 | 3 | 3 | 600 | 615 | 102.5% | 205 | 3 | 3 | 600 | 660 | 110% | 220 | 6 | 6 | 1200 | 1275 | 106.2% | 212.5
2026-01-14 | 3 | 3 | 600 | 675 | 112.5% | 225 | 3 | 3 | 600 | 525 | 87.5% | 175 | 6 | 6 | 1200 | 1200 | 100% | 200
2026-01-15 | 3 | 3 | 600 | 660 | 110% | 220 | 3 | 3 | 600 | 600 | 100% | 200 | 6 | 6 | 1200 | 1260 | 105% | 210
2026-01-16 | 3 | 3 | 600 | 210 | 35% | 70 | 3 | 3 | 600 | 615 | 102.5% | 205 | 6 | 6 | 1200 | 825 | 68.75% | 137.5
2026-01-17
2026-01-18
Week 2 | 3 | 3 | 3000 | 2730 | 91% | 182 | 3 | 3 | 3000 | 2835 | 94.5% | 189 | 6 | 6 | 6000 | 5565 | 92.75% | 185.5
2026-01-19 | 3 | 3 | 600 | 510 | 85% | 170 | 3 | 3 | 600 | 555 | 92.5% | 185 | 6 | 6 | 1200 | 1065 | 88.75% | 177.5
2026-01-20 | 3 | 3 | 600 | 465 | 77.5% | 155 | 3 | 3 | 600 | 705 | 117.5% | 235 | 6 | 6 | 1200 | 1170 | 97.5% | 195
2026-01-21 | 3 | 3 | 600 | 240 | 40% | 80 | 3 | 3 | 600 | 600 | 100% | 200 | 6 | 6 | 1200 | 840 | 70% | 140
2026-01-22 | 3 | 3 | 600 | 510 | 85% | 170 | 3 | 3 | 600 | 540 | 90% | 180 | 6 | 6 | 1200 | 1050 | 87.5% | 175
2026-01-23 | 3 | 3 | 600 | 360 | 60% | 120 | 3 | 3 | 600 | 540 | 90% | 180 | 6 | 6 | 1200 | 900 | 75% | 150
2026-01-24
2026-01-25
Week 3 | 3 | 3 | 3000 | 2085 | 69.5% | 139 | 3 | 3 | 3000 | 2940 | 98% | 196 | 6 | 6 | 6000 | 5025 | 83.75% | 167.5
2026-01-26 | 3 | 3 | 600 | 675 | 112.5% | 225 | 3 | 3 | 600 | 645 | 107.5% | 215 | 6 | 6 | 1200 | 1320 | 110% | 220
2026-01-27 | 3 | 3 | 600 | 660 | 110% | 220 | 3 | 3 | 600 | 690 | 115% | 230 | 6 | 6 | 1200 | 1350 | 112.5% | 225
2026-01-28 | 3 | 3 | 600 | 675 | 112.5% | 225 | 3 | 3 | 600 | 705 | 117.5% | 235 | 6 | 6 | 1200 | 1380 | 115% | 230
2026-01-29 | 3 | 3 | 600 | 630 | 105% | 210 | 3 | 3 | 600 | 690 | 115% | 230 | 6 | 6 | 1200 | 1320 | 110% | 220
2026-01-30 | 3 | 3 | 600 | 315 | 52.5% | 105 | 3 | 3 | 600 | 615 | 102.5% | 205 | 6 | 6 | 1200 | 930 | 77.5% | 155
2026-01-31
Week 4 | 3 | 3 | 3000 | 2955 | 98.5% | 197 | 3 | 3 | 3000 | 3345 | 111.5% | 223 | 6 | 6 | 6000 | 6300 | 105% | 210
Total | 3 | 3 | 12600 | 11293 | 89.63% | 178.4306 | 3 | 3 | 12600 | 12735 | 101.1% | 202.2083 | 6 | 6 | 25200 | 24028 | 95.35% | 190.3194
275
150
[5 empty] | 175 | 100
2850
1200
Formulas:
Week / Date = +[Week / Date, row above]+1

## E5SP TOP (Tape) (Feb)
Week / Date | Day Shift | [5 empty] | Night Shift | [5 empty] | Daily Total
| Workers |  | Production Qty |  |  | Output per Person | Workers |  | Production Qty |  |  | Output per Person | Workers |  | Production Qty |  |  | Output per Person
| Net Workers | Assigned | Plan | Actual | Achievement Rate |  | Net Workers | Assigned | Plan | Actual | Achievement Rate |  | Net Workers | Assigned | Plan | Actual | Achievement Rate
2026-02-01
2026-02-02 | 3 | 3 | 600 | 300 | 50% | 100 | 3 | 3 | 600 | 750 | 125% | 250 | 6 | 6 | 1200 | 1050 | 87.5% | 175
2026-02-03 | 3 | 3 | 600 | 690 | 115% | 230 | 3 | 3 | 600 | 660 | 110% | 220 | 6 | 6 | 1200 | 1350 | 112.5% | 225
2026-02-04 | 3 | 3 | 600 | 690 | 115% | 230 | 3 | 3 | 600 | 675 | 112.5% | 225 | 6 | 6 | 1200 | 1365 | 113.8% | 227.5
2026-02-05 | 3 | 3 | 600 | 810 | 135% | 270 | 3 | 3 | 600 | 525 | 87.5% | 175 | 6 | 6 | 1200 | 1335 | 111.2% | 222.5
2026-02-06 | 3 | 3 | 600 | 675 | 112.5% | 225 | 3 | 3 | 600 | 660 | 110% | 220 | 6 | 6 | 1200 | 1335 | 111.2% | 222.5
2026-02-07
2026-02-08
Week 1 | 3 | 3 | 3000 | 3165 | 105.5% | 211 | 3 | 3 | 3000 | 3270 | 109% | 218 | 6 | 6 | 6000 | 6435 | 107.2% | 214.5
2026-02-09 | 3 | 3 | 600 | 780 | 130% | 260 | 3 | 3 | 600 | 840 | 140% | 280 | 6 | 6 | 1200 | 1620 | 135% | 270
2026-02-10 | 3 | 3 | 600 | 675 | 112.5% | 225 | 3 | 3 | 600 | 645 | 107.5% | 215 | 6 | 6 | 1200 | 1320 | 110% | 220
2026-02-11 | 3 | 3 | 600 | 705 | 117.5% | 235 | 3 | 3 | 600 | 630 | 105% | 210 | 6 | 6 | 1200 | 1335 | 111.2% | 222.5
2026-02-12 | 3 | 3 | 600 | 450 | 75% | 150 | 3 | 3 | 600 | 540 | 90% | 180 | 6 | 6 | 1200 | 990 | 82.5% | 165
2026-02-13 | 3 | 3 | 600 | 765 | 127.5% | 255 | 3 | 3 | 600 | 510 | 85% | 170 | 6 | 6 | 1200 | 1275 | 106.2% | 212.5
2026-02-14 | 3 | 3 | 600 | 600 | 100% | 200 | 3 | 3 | 600 | 225 | 37.5% | 75 | 6 | 6 | 1200 | 825 | 68.75% | 137.5
2026-02-15
Week 2 | 3 | 3 | 3600 | 3975 | 110.4% | 220.8333 | 3 | 3 | 3600 | 3390 | 94.17% | 188.3333 | 6 | 6 | 7200 | 7365 | 102.3% | 204.5833
2026-02-16
2026-02-17
2026-02-18
2026-02-19 | 3 | 3 | 600 | 750 | 125% | 250 | 3 | 3 | 600 | 510 | 85% | 170 | 6 | 6 | 1200 | 1260 | 105% | 210
2026-02-20 | 3 | 3 | 600 | 660 | 110% | 220 | 3 | 3 | 600 | 675 | 112.5% | 225 | 6 | 6 | 1200 | 1335 | 111.2% | 222.5
2026-02-21 | 3 | 3 | 600 | 705 | 117.5% | 235 | [6 empty] | 3 | 3 | 600 | 705 | 117.5% | 235
2026-02-22
Week 3 | 3 | 3 | 1800 | 2115 | 117.5% | 235 | 3 | 3 | 1200 | 1185 | 98.75% | 197.5 | 5 | 5 | 3000 | 3300 | 110% | 222.5
2026-02-23 | 3 | 3 | 600 | 630 | 105% | 210 | 3 | 3 | 600 | 690 | 115% | 230 | 6 | 6 | 1200 | 1320 | 110% | 220
2026-02-24 | 3 | 3 | 600 | 840 | 140% | 280 | 3 | 3 | 600 | 525 | 87.5% | 175 | 6 | 6 | 1200 | 1365 | 113.8% | 227.5
2026-02-25 | 3 | 3 | 600 | 660 | 110% | 220 | 3 | 3 | 600 | 690 | 115% | 230 | 6 | 6 | 1200 | 1350 | 112.5% | 225
2026-02-26 | 3 | 3 | 600 | 660 | 110% | 220 | 3 | 3 | 600 | 690 | 115% | 230 | 6 | 6 | 1200 | 1350 | 112.5% | 225
2026-02-27 | 3 | 3 | 600 | 615 | 102.5% | 205 | 3 | 3 | 600 | 690 | 115% | 230 | 6 | 6 | 1200 | 1305 | 108.7% | 217.5
2026-02-28
Week 4 | 3 | 3 | 3000 | 3405 | 113.5% | 227 | 3 | 3 | 3000 | 3285 | 109.5% | 219 | 6 | 6 | 6000 | 6690 | 111.5% | 223
Total | 3 | 3 | 11400 | 12660 | 111.1% | 223.4583 | 3 | 3 | 10800 | 11130 | 103.1% | 205.7083 | 5.75 | 5.75 | 22200 | 23790 | 107.2% | 216.1458
Formulas:
Week / Date = +[Week / Date, row above]+1

## E5SP TOP (Tape) (Mar)
Week / Date | Day Shift | [5 empty] | Night Shift | [5 empty] | Daily Total
| Workers |  | Production Qty |  |  | Output per Person | Workers |  | Production Qty |  |  | Output per Person | Workers |  | Production Qty |  |  | Output per Person
| Net Workers | Assigned | Plan | Actual | Achievement Rate |  | Net Workers | Assigned | Plan | Actual | Achievement Rate |  | Net Workers | Assigned | Plan | Actual | Achievement Rate
2026-03-01
2026-03-02
2026-03-03 | 3 | 3 | 600 | 450 | 75% | 150 | 3 | 3 | 600 | 660 | 110% | 220 | 6 | 6 | 1200 | 1110 | 92.5% | 185
2026-03-04 | 3 | 3 | 600 | 615 | 102.5% | 205 | 3 | 3 | 600 | 660 | 110% | 220 | 6 | 6 | 1200 | 1275 | 106.2% | 212.5
2026-03-05 | 3 | 3 | 600 | 630 | 105% | 210 | 3 | 3 | 600 | 675 | 112.5% | 225 | 6 | 6 | 1200 | 1305 | 108.7% | 217.5
2026-03-06 | 3 | 3 | 600 | 645 | 107.5% | 215 | 3 | 3 | 600 | 705 | 117.5% | 235 | 6 | 6 | 1200 | 1350 | 112.5% | 225
2026-03-07
2026-03-08
Week 1 | 3 | 3 | 2400 | 2340 | 97.5% | 195 | 3 | 3 | 2400 | 2700 | 112.5% | 225 | 6 | 6 | 4800 | 5040 | 105% | 210
2026-03-09 | 3 | 3 | 600 | 675 | 112.5% | 225 | 3 | 3 | 600 | 690 | 115% | 230 | 6 | 6 | 1200 | 1365 | 113.8% | 227.5
2026-03-10 | 3 | 3 | 600 | 705 | 117.5% | 235 | 3 | 3 | 600 | 705 | 117.5% | 235 | 6 | 6 | 1200 | 1410 | 117.5% | 235
2026-03-11 | 3 | 3 | 600 | 675 | 112.5% | 225 | 3 | 3 | 600 | 675 | 112.5% | 225 | 6 | 6 | 1200 | 1350 | 112.5% | 225
2026-03-12 | 3 | 3 | 600 | 675 | 112.5% | 225 | 3 | 3 | 600 | 675 | 112.5% | 225 | 6 | 6 | 1200 | 1350 | 112.5% | 225
2026-03-13 | 3 | 3 | 600 | 600 | 100% | 200 | 3 | 3 | 600 | 615 | 102.5% | 205 | 6 | 6 | 1200 | 1215 | 101.2% | 202.5
2026-03-14 | 3 | 3 | 600 | 660 | 110% | 220 | [6 empty] | 3 | 3 | 600 | 660 | 110% | 220
2026-03-15
Week 2 | 3 | 3 | 3600 | 3990 | 110.8% | 221.6667 | 3 | 3 | 3000 | 3360 | 112% | 224 | 5.5 | 5.5 | 6600 | 7350 | 111.4% | 222.5
2026-03-16 | 3 | 3 | 600 | 645 | 107.5% | 215 | 3 | 3 | 600 | 675 | 112.5% | 225 | 6 | 6 | 1200 | 1320 | 110% | 220
2026-03-17 | 3 | 3 | 600 | 645 | 107.5% | 215 | 3 | 3 | 600 | 690 | 115% | 230 | 6 | 6 | 1200 | 1335 | 111.2% | 222.5
2026-03-18 | 3 | 3 | 600 | 690 | 115% | 230 | 3 | 3 | 600 | 705 | 117.5% | 235 | 6 | 6 | 1200 | 1395 | 116.3% | 232.5
2026-03-19 | 3 | 3 | 600 | 600 | 100% | 200 | 3 | 3 | 600 | 750 | 125% | 250 | 6 | 6 | 1200 | 1350 | 112.5% | 225
2026-03-20 | 3 | 3 | 600 | 45 | 7.5% | 15 | 3 | 3 | 600 | 630 | 105% | 210 | 6 | 6 | 1200 | 675 | 56.25% | 112.5
2026-03-21
2026-03-22
Week 3 | 3 | 3 | 3000 | 2625 | 87.5% | 175 | 3 | 3 | 3000 | 3450 | 115% | 230 | 6 | 6 | 6000 | 6075 | 101.2% | 202.5
2026-03-23 | 3 | 3 | 600 | 600 | 100% | 200 | 3 | 3 | 600 | 660 | 110% | 220 | 6 | 6 | 1200 | 1260 | 105% | 210
2026-03-24 | 3 | 3 | 600 | 630 | 105% | 210 | 3 | 3 | 600 | 90 | 15% | 30 | 6 | 6 | 1200 | 720 | 60% | 120
2026-03-25 | 3 | 3 | 600 | 630 | 105% | 210 | 3 | 3 | 600 | 645 | 107.5% | 215 | 6 | 6 | 1200 | 1275 | 106.2% | 212.5
2026-03-26 | 3 | 3 | 600 | 675 | 112.5% | 225 | 3 | 3 | 600 | 660 | 110% | 220 | 6 | 6 | 1200 | 1335 | 111.2% | 222.5
2026-03-27 | 3 | 3 | 600 | 540 | 90% | 180 | 3 | 3 | 600 | 570 | 95% | 190 | 6 | 6 | 1200 | 1110 | 92.5% | 185
2026-03-28
2026-03-29
Week 4 | 3 | 3 | 3000 | 3075 | 102.5% | 205 | 3 | 3 | 3000 | 2625 | 87.5% | 175 | 6 | 6 | 6000 | 5700 | 95% | 190
2026-03-30 | 3 | 3 | 600 | 360 | 60% | 120 | 3 | 3 | 600 | 495 | 82.5% | 165 | 6 | 6 | 1200 | 855 | 71.25% | 142.5
2026-03-31 | 3 | 3 | 600 | 360 | 60% | 120 | 3 | 3 | 600 | 465 | 77.5% | 155 | 6 | 6 | 1200 | 825 | 68.75% | 137.5
Week 5 | 3 | 3 | 1200 | 720 | 60% | 120 | 3 | 3 | 1200 | 960 | 80% | 160 | 6 | 6 | 2400 | 1680 | 70% | 140
Total | 3 | 3 | 13200 | 12750 | 96.59% | 183.3333 | 3 | 3 | 12600 | 13095 | 103.9% | 202.8 | 5.9 | 5.9 | 25800 | 25845 | 100.2% | 193
Formulas:
Week / Date = +[Week / Date, row above]+1

## E5SP TOP (Tape) (Apr)
Week / Date | Day Shift | [5 empty] | Night Shift | [5 empty] | Daily Total
| Workers |  | Production Qty |  |  | Output per Person | Workers |  | Production Qty |  |  | Output per Person | Workers |  | Production Qty |  |  | Output per Person
| Net Workers | Assigned | Plan | Actual | Achievement Rate |  | Net Workers | Assigned | Plan | Actual | Achievement Rate |  | Net Workers | Assigned | Plan | Actual | Achievement Rate
2026-04-01 | 3 | 3 | 600 | 375 | 62.5% | 125 | 3 | 3 | 600 | 405 | 67.5% | 135 | 6 | 6 | 1200 | 780 | 65% | 130
2026-04-02 | 3 | 3 | 600 | 450 | 75% | 150 | 3 | 3 | 600 | 465 | 77.5% | 155 | 6 | 6 | 1200 | 915 | 76.25% | 152.5
2026-04-03 | 3 | 3 | 600 | 390 | 65% | 130 | 3 | 3 | 600 | 465 | 77.5% | 155 | 6 | 6 | 1200 | 855 | 71.25% | 142.5
2026-04-04
2026-04-05 | 9 | 9 | 1200 | 1395 | 116.3% | 155 | [6 empty] | 9 | 9 | 1200 | 1395 | 116.3% | 155
Week 1 | 4.5 | 4.5 | 3000 | 2610 | 87% | 140 | 3 | 3 | 1800 | 1335 | 74.17% | 148.3333 | 6.75 | 6.75 | 4800 | 3945 | 82.19% | 145
2026-04-06 | [6 empty] | 3 | 3 | 600 | 270 | 45% | 90 | 3 | 3 | 600 | 270 | 45% | 90
2026-04-07 | 3 | 3 | 600 | 540 | 90% | 180 | 3 | 3 | 600 | 555 | 92.5% | 185 | 6 | 6 | 1200 | 1095 | 91.25% | 182.5
2026-04-08 | 3 | 3 | 600 | 570 | 95% | 190 | 3 | 3 | 600 | 180 | 30% | 60 | 6 | 6 | 1200 | 750 | 62.5% | 125
2026-04-09 | 3 | 3 | 600 | 510 | 85% | 170 | 3 | 3 | 600 | 435 | 72.5% | 145 | 6 | 6 | 1200 | 945 | 78.75% | 157.5
2026-04-10 | 3 | 3 | 600 | 615 | 102.5% | 205 | 3 | 3 | 600 | 630 | 105% | 210 | 6 | 6 | 1200 | 1245 | 103.8% | 207.5
2026-04-11
2026-04-12
Week 2 | 3 | 3 | 2400 | 2235 | 93.12% | 186.25 | 3 | 3 | 3000 | 2070 | 69% | 138 | 5.4 | 5.4 | 5400 | 4305 | 79.72% | 152.5
2026-04-13 | 4 | 4 | 600 | 180 | 30% | 45 | 4 | 4 | 600 | 690 | 115% | 172.5 | 8 | 8 | 1200 | 870 | 72.5% | 108.75
2026-04-14 | 4 | 4 | 600 | 210 | 35% | 52.5 | 4 | 4 | 600 | 840 | 140% | 210 | 8 | 8 | 1200 | 1050 | 87.5% | 131.25
2026-04-15 | 4 | 4 | 240 | 240 | 100% | 60 | 3 | 3 | 600 | 540 | 90% | 180 | 7 | 7 | 840 | 780 | 92.86% | 111.4286
2026-04-16 | 3 | 3 | 600 | 405 | 67.5% | 135 | 3 | 3 | 600 | 405 | 67.5% | 135 | 6 | 6 | 1200 | 810 | 67.5% | 135
2026-04-17 | 3 | 3 | 600 | 540 | 90% | 180 | 3 | 3 | 600 | 405 | 67.5% | 135 | 6 | 6 | 1200 | 945 | 78.75% | 157.5
2026-04-18 | [14 empty] | Non-operating
2026-04-19 | [14 empty] | Non-operating
Week 3 | 3.6 | 3.6 | 2640 | 1575 | 59.66% | 94.5 | 3.4 | 3.4 | 3000 | 2880 | 96% | 166.5 | 7 | 7 | 5640 | 4455 | 78.99% | 128.7857
2026-04-20 | 3 | 3 | 600 | 465 | 77.5% | 155 | 3 | 3 | 600 | 450 | 75% | 150 | 6 | 6 | 1200 | 915 | 76.25% | 152.5
2026-04-21 | 3 | 3 | 600 | 570 | 95% | 190 | 3 | 3 | 600 | 510 | 85% | 170 | 6 | 6 | 1200 | 1080 | 90% | 180
2026-04-22 | 3 | 3 | 600 | 690 | 115% | 230 | 3 | 3 | 600 | 390 | 65% | 130 | 6 | 6 | 1200 | 1080 | 90% | 180
2026-04-23 | 3 | 3 | 600 | 600 | 100% | 200 | 3 | 3 | 600 | 600 | 100% | 200 | 6 | 6 | 1200 | 1200 | 100% | 200
2026-04-24 | 3 | 3 | 600 | 600 | 100% | 200 | 3 | 3 | 600 | 585 | 97.5% | 195 | 6 | 6 | 1200 | 1185 | 98.75% | 197.5
2026-04-25
2026-04-26
Week 4 | 3 | 3 | 3000 | 2925 | 97.5% | 195 | 3 | 3 | 3000 | 2535 | 84.5% | 169 | 6 | 6 | 6000 | 5460 | 91% | 182
2026-04-27 | 3 |  | 600 |  | 0% |  | 3 |  | 600 |  | 0% |  | 6 |  | 1200
2026-04-28 | 3 |  | 600 |  | 0% |  | 3 |  | 600 |  | 0% |  | 6 |  | 1200
2026-04-29 | 3 |  | 600 |  | 0% |  | 3 |  | 600 |  | 0% |  | 6 |  | 1200
2026-04-30 | 3 |  | 600 |  | 0% |  | 3 |  | 600 |  | 0% |  | 6 |  | 1200
Week 5 | 3 |  | 2400 | 0 | 0% |  | 3 |  | 2400 | 0 | 0% |  | 6 |  | 4800 | 0 | 0%
Total | 3.42 | 3.525 | 13440 | 9345 | 69.53% | 153.9375 | 3.08 | 3.1 | 13200 | 8820 | 66.82% | 155.4583 | 6.23 | 6.2875 | 26640 | 18165 | 68.19% | 152.0714
Formulas:
Week / Date = +[Week / Date, row above]+1

## Under-Achievement Reasons
□ Issues & Under-Achievement Reasons
Date | Product | Achievement Rate | Reason | Countermeasure | Schedule | Person in Charge | Status
[7 empty] | Open | Close
E5SP TOP | 2026-01-01 | Non-operating
| 2026-01-02 | 103% | No notable issues
| 2026-01-03 | Non-operating
| 2026-01-04 | Non-operating
| 2026-01-05 | 101% | Tape release liner Y-axis fixture broken | Manual operation performed; normal operation resumed after repair | 2026-01-05 | C |  | O
| 2026-01-06 | 103% | No notable issues
| 2026-01-07 | 93% | SDI site visit: 4-hr manual tape application | On-site inspection completed; automation resumed normally | 2026-01-07 | B |  | O
| 2026-01-08 | 103% | No notable issues
| 2026-01-09 | 94% | Night shift: injection equipment issue caused 220-min stoppage; insufficient molded parts → automation target not met | Metering valve fault → valve disassembled, cleaned, and restarted | 2026-01-09 | A |  | O
| 2026-01-10 | Non-operating
| 2026-01-11 | Non-operating
| 2026-01-12 | 84% | Equipment fault caused work delay – tape dislodgement, product feed belt abnormality | Equipment origin reset; temporary belt fix applied; restarted | 2026-01-12 | A |  | O
| 2026-01-13 | 106% | No notable issues
| 2026-01-14 | 100% | Night shift: silicone release liner Y-axis error | Error resolved; restarted (170 min lost during repair) | 2026-01-14 | A |  | O
| 2026-01-15 | 105% | No notable issues
| 2026-01-16 | 69% | Injection machine stopped due to mold return issue | Mold repaired; injection machine restarted at 13:00 (300 min lost); automation restarted at 16:00 after part cooling (520 min lost) | 2026-01-16 | A |  | O
| 2026-01-17 | Non-operating
| 2026-01-18 | Non-operating
| 2026-01-19 | 89% | Injection machine controller main screen fault: 60 min lost; delayed machine start caused parts shortage: 200 min lost | Specialist contractor (Yudo) inspected fault; restarted | 2026-01-19 | A |  | O
| 2026-01-20 | 98% | Day shift: molded parts shortage caused 3-hr automation stoppage |  | 2026-01-20 | B |  | O
| 2026-01-21 | 70% | 3rd mold valve malfunction → equipment stopped; parts shortage caused 430-min automation stoppage | Switched to 2nd mold (injection machine stopped 250 min) | 2026-01-21 | A |  | O
| 2026-01-22 | 88% | After 2nd→3rd mold swap, 3rd mold valve fault triggered 3rd→2nd swap (150 min); parts shortage stoppage (170 min) | Normal operation after switching to 2nd mold | 2026-01-22 | A |  | O
| 2026-01-23 | 75% | 2nd mold gate protrusion repaired; 2nd→3rd mold swap; parts shortage caused 220-min automation loss | Normal operation after switching to 3rd mold | 2026-01-23 | A |  | O
| 2026-01-24 | Non-operating | Injection molding: 1,095 pcs produced (stored without tape application) | Week 5 of January (26–30): automation equipment stock replenishment | 2026-01-24 | A |  | O
| 2026-01-25 | Non-operating
| 2026-01-26 | 110% | No notable issues
| 2026-01-27 | 113% | No notable issues
| 2026-01-28 | 115% | No notable issues
| 2026-01-29 | 110% | Injection ejector block broken; equipment stopped (23:47) | Ejector unit vendor repair scheduled for Jan 30 (Fri) | 2026-01-30 | D | O
| 2026-01-30 | 78% | Injection ejector repair: 210 min lost | Equipment repaired at 11:30; restarted | 2026-01-31 | D |  | O
| 2026-01-31 | Non-operating
E5SP TOP (Automation) | 2026-02-01 | Non-operating
| 2026-02-02 | 88% | Silicone peeling X-axis wire broken and misaligned: 530 min lost | Equipment repaired; normal operation resumed | 2026-02-02 | C |  | O
| 2026-02-03 | 113% | No notable issues
| 2026-02-04 | 114% | No notable issues
| 2026-02-05 | 111% | No notable issues
| 2026-02-06 | 111% | No notable issues
| 2026-02-07 | Non-operating | Injection only; tape application deferred to next weekday. Mold issue (#2: ejector pin broken) → switched to #3. Mold issue (#3: ejector pin broken) → equipment stopped | Weekend injection: 405 pcs completed. Mold repair on Monday; equipment restart scheduled | 2026-02-09 | A | O
| 2026-02-08 | Non-operating
| 2026-02-09 | 135% | Exceeded target by processing previously unworked inventory |  | 2026-02-09 | B |  | O
| 2026-02-10 | 110% | No notable issues
| 2026-02-11 | 111% | No notable issues
| 2026-02-12 | 83% | Gate protrusion mold repaired; equipment restarted at 09:00; work started at 13:00 after part cooling: 300 min lost | Unused 1st mold hot runner replaced for production; 3rd mold hot runner inspected/repaired | 2026-02-12 | E |  | O
| 2026-02-13 | 106% | No notable issues
| 2026-02-14 | 69% | PET rotation left/right vacuum anomaly alarm | Origin reset and power cycle performed; restarted | 2026-02-14 | F |  | O
| 2026-02-15 | Non-operating
| 2026-02-16 | Non-operating
| 2026-02-17 | Non-operating
| 2026-02-18 | Non-operating
| 2026-02-19 | 105% | No notable issues
| 2026-02-20 | 111% | No notable issues
| 2026-02-21 | 118% | No notable issues
| 2026-02-22 | Non-operating
| 2026-02-23 | 110% | No notable issues
| 2026-02-24 | 114% | No notable issues
| 2026-02-25 | 113% | No notable issues
| 2026-02-26 | 113% | No notable issues
| 2026-02-27 | 109% | No notable issues
| 2026-02-28 | Non-operating
E5SP TOP (Automation) | 2026-03-01 | Non-operating
| 2026-03-02 | Non-operating
| 2026-03-03 | 96% | Silicone shot section Y-axis and Z-axis failure | Equipment repaired and restarted | 2026-03-03 | C |  | O
| 2026-03-04 | 106% | No notable issues
| 2026-03-05 | 109% | No notable issues
| 2026-03-06 | 113% | No notable issues
| 2026-03-07 | Non-operating
| 2026-03-08 | Non-operating
| 2026-03-09 | 113.8% | No notable issues
| 2026-03-10 | 118% | No notable issues
| 2026-03-11 | 113% | No notable issues
| 2026-03-12 | 113% | No notable issues
| 2026-03-13 | 101% | No notable issues
| 2026-03-14 | 110% | No notable issues
| 2026-03-15 | Non-operating
| 2026-03-16 | 113% | No notable issues
| 2026-03-17 | 115% | No notable issues
| 2026-03-18 | 116% | No notable issues
| 2026-03-19 | 113% | No notable issues
| 2026-03-20 | 56% | Injection-molded parts shortage due to mid-week overproduction | Day-shift automation equipment stopped
| 2026-03-21 | Non-operating
| 2026-03-22 | Non-operating
| 2026-03-23 | 105% | No notable issues
| 2026-03-24 | 60% | Injection-molded parts shortage | Night-shift automation equipment stopped | 2026-03-24 | B |  | O
| 2026-03-25 | 106% | No notable issues
| 2026-03-26 | 111% | No notable issues
| 2026-03-27 | 93% | PET tape defect scraps increased (170 pcs) – dislodged: 32, wrinkled: 44, folded: 90, other: 4 | PET tape issue identified; improvement requested from supplier | 2026-03-27 | B |  | O
| 2026-03-28 | Non-operating
| 2026-03-29 | Non-operating
| 2026-03-30 | 71% | Injection-molded parts shortage으로 자동화 설비 정지 | Automation cycle faster than injection C/T; flexible operation applied | 2026-03-30 | B |  | O
| 2026-03-31 | 69% | Tape dislodgement; improved tape sample testing | Equipment inspected and improved parts tested; normal operation resumed | 2026-03-31 | A |  | O
E5SP TOP (Automation) | 2026-04-01 | 65% | Tape release liner peeling fault and excessive micro-stoppages | Equipment and tape inspected; restarted | 2026-04-01 | E |  | O
| 2026-04-02 | 76% | Silicone process product transfer jig movement error (delayed resolution) | Equipment inspected; restarted (power cycled; transfer jig position checked) | 2026-04-02 | G |  | O
| 2026-04-03 | 71% | Tape process suction fault; equipment stopped | Equipment inspected; right-side suction pad replaced; restarted | 2026-04-03 | E |  | O
| 2026-04-04 | Non-operating
| 2026-04-05 | 116% | No notable issues | Manual silicone tape operation in progress
| 2026-04-06 | 45% | Safety incident on automation equipment; workers refused to operate automation | Night-shift automation stopped; manual work performed; automation issue improvements implemented | 2026-04-06 | C |  | O
| 2026-04-07 | 91% | Robot suction failure | Repaired and restarted (50 min lost) | 2026-04-07 | E |  | O
| 2026-04-08 | 63% | Tape right-side vacuum fault; equipment stopped | Day-shift inspection on the 9th; restarted | 2026-04-09 | C |  | O
| 2026-04-09 | 79% | Tape right-side vacuum fault; equipment stopped | Day-shift inspection on the 9th; restarted (200 min lost) | 2026-04-09 | C |  | O
| 2026-04-10 | 104% | No notable issues
| 2026-04-11 | Non-operating
| 2026-04-12 | Non-operating
| 2026-04-13 | 73% | E5SP TOP Sunday inspection backlog (315 pcs) completed; E5S TOP inspection proceeded | 100% achievement when E5SP TOP 315 pcs included | 2026-04-13 | B |  | O
| 2026-04-14 | 88% | Day shift: one worker took half-day PM leave; final output reduced | E5S TOP tape application completed around 17:00 on the 15th | 2026-04-14 | B |  | O
| 2026-04-15 | 93% | No notable issues | Day shift E5S TOP completed; night shift E5SP automation started | 2026-04-15 | E |  | O
| 2026-04-16 | 68% | Injection-molded parts shortage due to injection machine issue
| 2026-04-17 | 79% | Injection-molded parts shortage due to injection machine issue
| 2026-04-18 | Non-operating
| 2026-04-19 | Non-operating
| 2026-04-20 | 76% | Injection-molded parts shortage due to injection machine issue
| 2026-04-21 | 90% | No notable issues other than micro-stoppages
| 2026-04-22 | 90% | No notable issues other than micro-stoppages
| 2026-04-23 | 100% | No notable issues
| 2026-04-24 | 99% | No notable issues
2026-04-25
2026-04-26
2026-04-27
2026-04-28
2026-04-29
2026-04-30
Formulas:
Product = +[Product, row above]+1

## Automation Results (Jan-Apr)
□ Tape Auto-Applicator Production Results
□ Daily Results | [108 empty] | □ 주별 Total | [19 empty] | □ 주별 평균 | [19 empty] | □ 월별 Total |  |  |  |  | □ 월별 평균
Category | [109 empty] | 1-1W | 1-2W | 1-3W | 1-4W | 1-5W | 2-1W | 2-2W | 2-3W | 2-4W | 3-1W | 3-2W | 3-3W | 3-4W | 3-5W | 4-1W | 4-2W | 4-3W | 4-4W | 4-5W |  | 1-1W | 1-2W | 1-3W | 1-4W | 1-5W | 2-1W | 2-2W | 2-3W | 2-4W | 3-1W | 3-2W | 3-3W | 3-4W | 3-5W | 4-1W | 4-2W | 4-3W | 4-4W | 4-5W |  | 1월 | 2월 | 3월 | 4월 |  | 1월 | 2월 | 3월 | 4월 | time axis 2026-01-02 to 2026-04-30
Total | Input Qty | 1273 | 1030 | 1247 | 1104 | 1249 | 1143 | 1069 | 1291 | 1217 | 1283 | 852 | 1090 | 1188 | 852 | 1058 | 917 | 1332 | 1366 | 1396 | 1342 | 944 | 1064 | 1361 | 1375 | 1359 | 1345 | 1406 | 1337 | 1341 | 1006 | 1316 | 845 | 0 | 0 | 0 | 0 | 1274 | 1354 | 706 | 0 | 1347 | 1372 | 1360 | 1365 | 1306 | 0 | 0 | 0 | 1118 | 1316 | 1357 | 1364 | 0 | 0 | 1371 | 1417 | 1357 | 1355 | 1220 | 666 | 0 | 1337 | 1348 | 1403 | 1356 | 687 | 0 | 0 | 1273 | 744 | 1293 | 1365 | 1280 | 0 | 0 | 900 | 917 | 831 | 940 | 918 | 0 | 0 | 0 | 1123 | 785 | 962 | 1257 | 0 | 0 | 0 | 0 | 575 | 849 | 993 | 0 | 0 | 985 | 1124 | 1126 | 1224 | 1203 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1273 | 5773 | 5712 | 5105 | 6380 | 6504 | 7251 | 3334 | 6750 | 5155 | 7386 | 6131 | 5955 | 1817 | 2689 | 4127 | 2417 | 5662 | 4677 |  | 1273 | 1154.6 | 1142.4 | 1021 | 1276 | 1300.8 | 1208.5 | 1335.5 | 1125 | 1288.75 | 1343.3 | 1226.2 | 1191 | 908.5 | 896.3333 | 1031.75 | 960.8333 | 0 | 0 |  | 24243 | 23839 | 26444 | 19572 |  | 1173.4 | 1242.45 | 1191.55 | 962.9722
| Good Qty | 1230 | 990 | 1230 | 1065 | 1230 | 1095 | 1020 | 1275 | 1200 | 1260 | 825 | 1065 | 1170 | 840 | 1050 | 900 | 1320 | 1350 | 1380 | 1320 | 930 | 1050 | 1350 | 1365 | 1335 | 1335 | 1395 | 1320 | 1335 | 990 | 1275 | 825 | 0 | 0 | 0 | 0 | 1260 | 1335 | 705 | 0 | 1320 | 1365 | 1350 | 1350 | 1305 | 0 | 0 | 0 | 1110 | 1275 | 1305 | 1350 | 0 | 0 | 1365 | 1410 | 1350 | 1350 | 1215 | 660 | 0 | 1320 | 1335 | 1395 | 1350 | 675 | 0 | 0 | 1260 | 720 | 1275 | 1335 | 1110 | 0 | 0 | 855 | 825 | 780 | 915 | 855 | 0 | 0 | 0 | 1095 | 750 | 945 | 1245 | 0 | 0 | 0 | 0 | 540 | 810 | 945 | 0 | 0 | 915 | 1080 | 1080 | 1200 | 1185 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1230 | 5610 | 5580 | 5025 | 6300 | 6435 | 7140 | 3300 | 6690 | 5040 | 7350 | 6075 | 5700 | 1680 | 2550 | 4035 | 2295 | 5460 | 4545 |  | 1230 | 1122 | 1116 | 1005 | 1260 | 1287 | 1190 | 1322.5 | 1115 | 1260 | 1337 | 1215 | 1140 | 840 | 850 | 1008.75 | 915 | 0 | 0 |  | 23745 | 23565 | 25845 | 18885 |  | 1146.6 | 1228.625 | 1158.4 | 924.5833
| In-Process Defects | 74 | 75 | 51 | 79 | 43 | 97 | 82 | 48 | 47 | 45 | 43 | 138 | 67 | 112 | 51 | 33 | 53 | 42 | 25 | 59 | 17 | 30 | 31 | 18 | 36 | 28 | 25 | 40 | 30 | 45 | 56 | 26 | 0 | 0 | 0 | 0 | 46 | 34 | 10 | 0 | 50 | 47 | 32 | 28 | 17 | 0 | 0 | 0 | 33 | 92 | 72 | 27 | 0 | 0 | 36 | 28 | 27 | 26 | 32 | 17 | 0 | 35 | 32 | 17 | 14 | 12 | 0 | 0 | 26 | 41 | 65 | 41 | 198 | 0 | 0 | 45 | 92 | 99 | 83 | 73 | 0 | 0 | 0 | 43 | 35 | 17 | 12 | 0 | 0 | 0 | 0 | 35 | 74 | 93 | 0 | 0 | 70 | 76 | 71 | 39 | 30 | 0 | 0 | 0 | 0 | 0 | 0 |  | 74 | 345 | 265 | 401 | 196 | 143 | 222 | 90 | 174 | 224 | 166 | 110 | 371 | 137 | 255 | 107 | 202 | 286 | 216 |  | 74 | 69 | 53 | 80.2 | 39.2 | 28.6 | 37 | 35.6667 | 29 | 56 | 30.4 | 22 | 74.2 | 68.5 | 85 | 26.75 | 85.8333 | 0 | 0 |  | 1281 | 629 | 1008 | 1066 |  | 63.08 | 32.5667 | 50.22 | 65.8611
| Final Defects | 43 | 40 | 17 | 39 | 19 | 48 | 49 | 16 | 17 | 23 | 27 | 25 | 18 | 12 | 8 | 17 | 12 | 16 | 16 | 22 | 14 | 14 | 11 | 10 | 24 | 10 | 11 | 17 | 6 | 16 | 41 | 20 | 0 | 0 | 0 | 0 | 14 | 19 | 1 | 0 | 27 | 7 | 10 | 15 | 1 | 0 | 0 | 0 | 8 | 41 | 52 | 14 | 0 | 0 | 6 | 7 | 7 | 5 | 5 | 6 | 0 | 17 | 13 | 8 | 6 | 12 | 0 | 0 | 13 | 24 | 15 | 30 | 170 | 0 | 0 | 26 | 74 | 51 | 25 | 63 | 0 | 0 | 0 | 28 | 35 | 17 | 12 | 0 | 0 | 0 | 0 | 35 | 39 | 48 | 0 | 0 | 70 | 44 | 45 | 24 | 18 | 0 | 0 | 0 | 0 | 0 | 0 |  | 43 | 163 | 132 | 80 | 80 | 69 | 111 | 34 | 60 | 115 | 36 | 56 | 252 | 100 | 139 | 92 | 122 | 201 | 131 |  | 43 | 32.6 | 26.4 | 16 | 16 | 13.8 | 18.5 | 13 | 10 | 28.75 | 6.3 | 11.2 | 50.4 | 50 | 46.3333 | 23 | 45.8333 | 0 | 0 |  | 498 | 274 | 559 | 685 |  | 26.8 | 13.825 | 29.33 | 38.3889
| In-Process Defect Rate | 5.813% | 7.282% | 4.09% | 7.156% | 3.443% | 8.486% | 7.671% | 3.718% | 3.862% | 3.507% | 5.047% | 12.66% | 5.64% | 13.15% | 4.82% | 3.599% | 3.979% | 3.075% | 1.791% | 4.396% | 1.801% | 2.82% | 2.278% | 1.309% | 2.649% | 2.082% | 1.778% | 2.992% | 2.237% | 4.473% | 4.255% | 3.077% |  |  |  |  | 3.611% | 2.511% | 1.416% |  | 3.712% | 3.426% | 2.353% | 2.051% | 1.302% |  |  |  | 2.952% | 6.991% | 5.306% | 1.979% |  |  | 2.626% | 1.976% | 1.99% | 1.919% | 2.623% | 2.553% |  | 2.618% | 2.374% | 1.212% | 1.032% | 1.747% |  |  | 2.042% | 5.511% | 5.027% | 3.004% | 15.47% |  |  | 5% | 10.03% | 11.91% | 8.83% | 7.952% |  |  |  | 3.829% | 4.459% | 1.767% | 0.9547% |  |  |  |  | 6.087% | 8.716% | 9.366% |  |  | 7.107% | 6.762% | 6.306% | 3.186% | 2.494% | [7 empty] | 5.813% | 5.976% | 4.639% | 7.855% | 3.072% | 2.199% | 3.062% | 2.699% | 2.578% | 4.345% | 2.247% | 1.794% | 6.23% | 7.54% | 9.483% | 2.593% | 8.357% | 5.051% | 4.618% |  | 5.813% | 5.976% | 4.639% | 7.855% | 3.072% | 2.199% | 3.062% | 2.671% | 2.578% | 4.345% | 2.263% | 1.794% | 6.23% | 7.54% | 9.483% | 2.593% | 8.933% |  |  |  | 5.284% | 2.639% | 3.812% | 5.447% |  | 5.376% | 2.621% | 4.215% | 6.839%
| Final Defect Rate | 3.378% | 3.883% | 1.363% | 3.533% | 1.521% | 4.199% | 4.584% | 1.239% | 1.397% | 1.793% | 3.169% | 2.294% | 1.515% | 1.408% | 0.7561% | 1.854% | 0.9009% | 1.171% | 1.146% | 1.639% | 1.483% | 1.316% | 0.8082% | 0.7273% | 1.766% | 0.7435% | 0.7824% | 1.272% | 0.4474% | 1.59% | 3.116% | 2.367% |  |  |  |  | 1.099% | 1.403% | 0.1416% |  | 2.004% | 0.5102% | 0.7353% | 1.099% | 0.07657% |  |  |  | 0.7156% | 3.116% | 3.832% | 1.026% |  |  | 0.4376% | 0.494% | 0.5158% | 0.369% | 0.4098% | 0.9009% |  | 1.272% | 0.9644% | 0.5702% | 0.4425% | 1.747% |  |  | 1.021% | 3.226% | 1.16% | 2.198% | 13.28% |  |  | 2.889% | 8.07% | 6.137% | 2.66% | 6.863% |  |  |  | 2.493% | 4.459% | 1.767% | 0.9547% |  |  |  |  | 6.087% | 4.594% | 4.834% |  |  | 7.107% | 3.915% | 3.996% | 1.961% | 1.496% | [7 empty] | 3.378% | 2.823% | 2.311% | 1.567% | 1.254% | 1.061% | 1.531% | 1.02% | 0.8889% | 2.231% | 0.4874% | 0.9134% | 4.232% | 5.504% | 5.169% | 2.229% | 5.048% | 3.55% | 2.801% |  | 3.378% | 2.823% | 2.311% | 1.567% | 1.254% | 1.061% | 1.531% | 0.9734% | 0.8889% | 2.231% | 0.469% | 0.9134% | 4.232% | 5.504% | 5.169% | 2.229% | 4.77% |  |  |  | 2.054% | 1.149% | 2.114% | 3.5% |  | 2.284% | 1.113% | 2.461% | 3.987%
Day Shift | Input Qty | 605 | 366 | 590 | 474 | 606 | 657 | 583 | 628 | 681 | 667 | 214 | 530 | 473 | 245 | 515 | 368 | 684 | 669 | 685 | 642 | 319 | 300 | 678 | 692 | 678 | 681 | 707 | 682 | 707 | 348 | 643 | 567 |  |  |  |  | 608 | 675 | 706 |  | 655 | 695 | 669 | 669 | 616 | 0 |  |  | 456 | 642 | 671 | 656 |  |  | 680 | 709 | 677 | 680 | 605 | 666 |  | 657 | 648 | 693 | 690 | 0 |  |  | 588 | 648 | 641 | 693 | 649 |  |  | 364 | 407 | 439 | 465 | 425 |  |  |  | 563 | 580 | 526 | 620 | [5 empty] | 418 | 513 |  |  | 413 | 559 | 564 | 611 | 591 | [7 empty] | 605 | 2693 | 2773 | 2131 | 2999 | 3029 | 3654 | 1989 | 3304 | 2425 | 4017 | 2688 | 3219 | 771 | 1329 | 2289 | 931 | 2738 | 2325 |  | 605 | 538.6 | 554.6 | 426.2 | 599.8 | 605.8 | 609 | 663 | 550.6667 | 606.25 | 669.5 | 537.6 | 643.8 | 385.5 | 443 | 572.25 | 465.5 |  |  |  | 11201 | 11976 | 13120 | 9612 |  | 544.84 | 607.1167 | 568.53 | 493.5833
| Good Qty | 585 | 345 | 585 | 465 | 600 | 645 | 570 | 615 | 675 | 660 | 210 | 510 | 465 | 240 | 510 | 360 | 675 | 660 | 675 | 630 | 315 | 300 | 675 | 690 | 660 | 675 | 705 | 675 | 705 | 345 | 615 | 555 |  |  |  |  | 600 | 660 | 705 |  | 630 | 690 | 660 | 660 | 615 | 0 |  |  | 450 | 615 | 630 | 645 |  |  | 675 | 705 | 675 | 675 | 600 | 660 |  | 645 | 645 | 690 | 690 | 0 |  |  | 585 | 630 | 630 | 675 | 540 |  |  | 360 | 360 | 405 | 450 | 390 |  |  |  | 555 | 570 | 510 | 615 | [5 empty] | 405 | 495 |  |  | 390 | 540 | 540 | 600 | 585 | [7 empty] | 585 | 2640 | 2730 | 2085 | 2955 | 3000 | 3600 | 1965 | 3255 | 2340 | 3990 | 2670 | 3060 | 720 | 1245 | 2250 | 900 | 2655 | 2265 |  | 585 | 528 | 546 | 417 | 591 | 600 | 600 | 655 | 542.5 | 585 | 665 | 534 | 612 | 360 | 415 | 562.5 | 450 |  |  |  | 10995 | 11820 | 12780 | 9315 |  | 533.4 | 599.375 | 551.2 | 475.8333
| In-Process Defects | 41 | 28 | 24 | 24 | 16 | 47 | 32 | 24 | 16 | 17 | 10 | 66 | 35 | 24 | 40 | 11 | 26 | 25 | 14 | 26 | 7 | 4 | 16 | 6 | 23 | 14 | 8 | 11 | 16 | 15 | 31 | 14 |  |  |  |  | 24 | 22 | 10 |  | 28 | 19 | 21 | 12 | 8 | 0 |  |  | 14 | 69 | 46 | 18 |  |  | 19 | 11 | 8 | 12 | 17 | 17 |  | 23 | 17 | 8 | 5 | 0 |  |  | 15 | 35 | 58 | 29 | 137 |  |  | 4 | 47 | 82 | 15 | 35 |  |  |  | 23 | 10 | 16 | 5 | [5 empty] | 48 | 63 |  |  | 23 | 51 | 49 | 26 | 18 | [7 empty] | 41 | 139 | 99 | 176 | 98 | 63 | 95 | 56 | 88 | 147 | 84 | 53 | 274 | 51 | 132 | 54 | 111 | 167 | 144 |  | 41 | 27.8 | 19.8 | 35.2 | 19.6 | 12.6 | 15.8333 | 18.6667 | 14.6667 | 36.75 | 14 | 10.6 | 54.8 | 25.5 | 44 | 13.5 | 55.5 |  |  |  | 553 | 302 | 609 | 608 |  | 28.68 | 15.4417 | 28.33 | 37.6667
| Final Defects | 20 | 21 | 5 | 9 | 6 | 12 | 13 | 13 | 6 | 7 | 4 | 20 | 8 | 5 | 5 | 8 | 9 | 9 | 10 | 12 | 4 | 0 | 3 | 2 | 18 | 6 | 2 | 7 | 2 | 3 | 28 | 12 |  |  |  |  | 8 | 15 | 1 |  | 25 | 5 | 9 | 9 | 1 | 0 |  |  | 6 | 27 | 41 | 11 |  |  | 5 | 4 | 2 | 5 | 5 | 6 |  | 12 | 3 | 3 | 0 | 0 |  |  | 3 | 18 | 11 | 18 | 109 |  |  | 4 | 47 | 34 | 15 | 35 |  |  |  | 8 | 10 | 16 | 5 | [5 empty] | 13 | 18 |  |  | 23 | 19 | 24 | 11 | 6 | [7 empty] | 20 | 53 | 43 | 46 | 44 | 29 | 54 | 24 | 49 | 85 | 27 | 18 | 159 | 51 | 84 | 39 | 31 | 83 | 60 |  | 20 | 10.6 | 8.6 | 9.2 | 8.8 | 5.8 | 9 | 8 | 8.1667 | 21.25 | 4.5 | 3.6 | 31.8 | 25.5 | 28 | 9.75 | 15.5 |  |  |  | 206 | 156 | 340 | 297 |  | 11.44 | 7.7417 | 17.33 | 17.75
| In-Process Defect Rate | 6.777% | 7.65% | 4.068% | 5.063% | 2.64% | 7.154% | 5.489% | 3.822% | 2.349% | 2.549% | 4.673% | 12.45% | 7.4% | 9.796% | 7.767% | 2.989% | 3.801% | 3.737% | 2.044% | 4.05% | 2.194% | 1.333% | 2.36% | 0.8671% | 3.392% | 2.056% | 1.132% | 1.613% | 2.263% | 4.31% | 4.821% | 2.469% |  |  |  |  | 3.947% | 3.259% | 1.416% |  | 4.275% | 2.734% | 3.139% | 1.794% | 1.299% |  |  |  | 3.07% | 10.75% | 6.855% | 2.744% |  |  | 2.794% | 1.551% | 1.182% | 1.765% | 2.81% | 2.553% |  | 3.501% | 2.623% | 1.154% | 0.7246% |  |  |  | 2.551% | 5.401% | 9.048% | 4.185% | 21.11% |  |  | 1.099% | 11.55% | 18.68% | 3.226% | 8.235% |  |  |  | 4.085% | 1.724% | 3.042% | 0.8065% | [5 empty] | 11.48% | 12.28% |  |  | 5.569% | 9.123% | 8.688% | 4.255% | 3.046% | [7 empty] | 6.777% | 5.162% | 3.57% | 8.259% | 3.268% | 2.08% | 2.6% | 2.815% | 2.663% | 6.062% | 2.091% | 1.972% | 8.512% | 6.615% | 9.932% | 2.359% | 11.92% | 6.099% | 6.194% |  | 6.777% | 5.162% | 3.57% | 8.259% | 3.268% | 2.08% | 2.6% | 2.815% | 2.663% | 6.062% | 2.091% | 1.972% | 8.512% | 6.615% | 9.932% | 2.359% | 11.92% |  |  |  | 4.937% | 2.522% | 4.642% | 6.325% |  | 5.264% | 2.543% | 4.983% | 7.631%
| Final Defect Rate | 3.306% | 5.738% | 0.8475% | 1.899% | 0.9901% | 1.826% | 2.23% | 2.07% | 0.8811% | 1.049% | 1.869% | 3.774% | 1.691% | 2.041% | 0.9709% | 2.174% | 1.316% | 1.345% | 1.46% | 1.869% | 1.254% | 0% | 0.4425% | 0.289% | 2.655% | 0.8811% | 0.2829% | 1.026% | 0.2829% | 0.8621% | 4.355% | 2.116% |  |  |  |  | 1.316% | 2.222% | 0.1416% |  | 3.817% | 0.7194% | 1.345% | 1.345% | 0.1623% |  |  |  | 1.316% | 4.206% | 6.11% | 1.677% |  |  | 0.7353% | 0.5642% | 0.2954% | 0.7353% | 0.8264% | 0.9009% |  | 1.826% | 0.463% | 0.4329% | 0% |  |  |  | 0.5102% | 2.778% | 1.716% | 2.597% | 16.8% |  |  | 1.099% | 11.55% | 7.745% | 3.226% | 8.235% |  |  |  | 1.421% | 1.724% | 3.042% | 0.8065% | [5 empty] | 3.11% | 3.509% |  |  | 5.569% | 3.399% | 4.255% | 1.8% | 1.015% | [7 empty] | 3.306% | 1.968% | 1.551% | 2.159% | 1.467% | 0.9574% | 1.478% | 1.207% | 1.483% | 3.505% | 0.6721% | 0.6696% | 4.939% | 6.615% | 6.321% | 1.704% | 3.33% | 3.031% | 2.581% |  | 3.306% | 1.968% | 1.551% | 2.159% | 1.467% | 0.9574% | 1.478% | 1.207% | 1.483% | 3.505% | 0.6721% | 0.6696% | 4.939% | 6.615% | 6.321% | 1.704% | 3.33% |  |  |  | 1.839% | 1.303% | 2.591% | 3.09% |  | 2.1% | 1.275% | 3.048% | 3.596%
Night Shift | Input Qty | 668 | 664 | 657 | 630 | 643 | 486 | 486 | 663 | 536 | 616 | 638 | 560 | 715 | 607 | 543 | 549 | 648 | 697 | 711 | 700 | 625 | 764 | 683 | 683 | 681 | 664 | 699 | 655 | 634 | 658 | 673 | 278 |  |  |  |  | 666 | 679 |  |  | 692 | 677 | 691 | 696 | 690 | 0 |  |  | 662 | 674 | 686 | 708 |  |  | 691 | 708 | 680 | 675 | 615 |  |  | 680 | 700 | 710 | 666 | 687 |  |  | 685 | 96 | 652 | 672 | 631 |  |  | 536 | 510 | 392 | 475 | 493 |  |  |  | 560 | 205 | 436 | 637 |  |  |  |  | 575 | 431 | 480 |  |  | 572 | 565 | 562 | 613 | 612 | [7 empty] | 668 | 3080 | 2939 | 2974 | 3381 | 3475 | 3597 | 1345 | 3446 | 2730 | 3369 | 3443 | 2736 | 1046 | 1360 | 1838 | 1486 | 2924 | 2352 |  | 668 | 616 | 587.8 | 594.8 | 676.2 | 695 | 599.5 | 672.5 | 574.3333 | 682.5 | 673.8 | 688.6 | 547.2 | 523 | 453.3333 | 459.5 | 495.3333 |  |  |  | 13042 | 11863 | 13324 | 9960 |  | 628.56 | 635.3333 | 623.02 | 469.3889
| Good Qty | 645 | 645 | 645 | 600 | 630 | 450 | 450 | 660 | 525 | 600 | 615 | 555 | 705 | 600 | 540 | 540 | 645 | 690 | 705 | 690 | 615 | 750 | 675 | 675 | 675 | 660 | 690 | 645 | 630 | 645 | 660 | 270 |  |  |  |  | 660 | 675 |  |  | 690 | 675 | 690 | 690 | 690 | 0 |  |  | 660 | 660 | 675 | 705 |  |  | 690 | 705 | 675 | 675 | 615 |  |  | 675 | 690 | 705 | 660 | 675 |  |  | 675 | 90 | 645 | 660 | 570 |  |  | 495 | 465 | 375 | 465 | 465 |  |  |  | 540 | 180 | 435 | 630 |  |  |  |  | 540 | 405 | 450 |  |  | 525 | 540 | 540 | 600 | 600 | [7 empty] | 645 | 2970 | 2850 | 2940 | 3345 | 3435 | 3540 | 1335 | 3435 | 2700 | 3360 | 3405 | 2640 | 960 | 1305 | 1785 | 1395 | 2805 | 2280 |  | 645 | 594 | 570 | 588 | 669 | 687 | 590 | 667.5 | 572.5 | 675 | 672 | 681 | 528 | 480 | 435 | 446.25 | 465 |  |  |  | 12750 | 11745 | 13065 | 9570 |  | 613.2 | 629.25 | 607.2 | 448.75
| In-Process Defects | 33 | 47 | 27 | 55 | 27 | 50 | 50 | 24 | 31 | 28 | 33 | 72 | 32 | 88 | 11 | 22 | 27 | 17 | 11 | 33 | 10 | 26 | 15 | 12 | 13 | 14 | 17 | 29 | 14 | 30 | 25 | 12 |  |  |  |  | 22 | 12 |  |  | 22 | 28 | 11 | 16 | 9 | 0 |  |  | 19 | 23 | 26 | 9 |  |  | 17 | 17 | 19 | 14 | 15 |  |  | 12 | 15 | 9 | 9 | 12 |  |  | 11 | 6 | 7 | 12 | 61 |  |  | 41 | 45 | 17 | 68 | 38 |  |  |  | 20 | 25 | 1 | 7 |  |  |  |  | 35 | 26 | 30 |  |  | 47 | 25 | 22 | 13 | 12 | [7 empty] | 33 | 206 | 166 | 225 | 98 | 80 | 127 | 34 | 86 | 77 | 82 | 57 | 97 | 86 | 123 | 53 | 91 | 119 | 72 |  | 33 | 41.2 | 33.2 | 45 | 19.6 | 16 | 21.1667 | 17 | 14.3333 | 19.25 | 16.4 | 11.4 | 19.4 | 43 | 41 | 13.25 | 30.3333 |  |  |  | 728 | 327 | 399 | 458 |  | 34.4 | 17.125 | 21.89 | 28.1944
| Final Defects | 23 | 19 | 12 | 30 | 13 | 36 | 36 | 3 | 11 | 16 | 23 | 5 | 10 | 7 | 3 | 9 | 3 | 7 | 6 | 10 | 10 | 14 | 8 | 8 | 6 | 4 | 9 | 10 | 4 | 13 | 13 | 8 |  |  |  |  | 6 | 4 |  |  | 2 | 2 | 1 | 6 | 0 | 0 |  |  | 2 | 14 | 11 | 3 |  |  | 1 | 3 | 5 | 0 | 0 |  |  | 5 | 10 | 5 | 6 | 12 |  |  | 10 | 6 | 4 | 12 | 61 |  |  | 22 | 27 | 17 | 10 | 28 |  |  |  | 20 | 25 | 1 | 7 |  |  |  |  | 35 | 26 | 30 |  |  | 47 | 25 | 21 | 13 | 12 | [7 empty] | 23 | 110 | 89 | 34 | 36 | 40 | 57 | 10 | 11 | 30 | 9 | 38 | 93 | 49 | 55 | 53 | 91 | 118 | 71 |  | 23 | 22 | 17.8 | 6.8 | 7.2 | 8 | 9.5 | 5 | 1.8333 | 7.5 | 1.8 | 7.6 | 18.6 | 24.5 | 18.3333 | 13.25 | 30.3333 |  |  |  | 292 | 118 | 219 | 388 |  | 15.36 | 6.0833 | 12 | 20.6389
| In-Process Defect Rate | 4.94% | 7.078% | 4.11% | 8.73% | 4.199% | 10.29% | 10.29% | 3.62% | 5.784% | 4.545% | 5.172% | 12.86% | 4.476% | 14.5% | 2.026% | 4.007% | 4.167% | 2.439% | 1.547% | 4.714% | 1.6% | 3.403% | 2.196% | 1.757% | 1.909% | 2.108% | 2.432% | 4.427% | 2.208% | 4.559% | 3.715% | 4.317% |  |  |  |  | 3.303% | 1.767% |  |  | 3.179% | 4.136% | 1.592% | 2.299% | 1.304% |  |  |  | 2.87% | 3.412% | 3.79% | 1.271% |  |  | 2.46% | 2.401% | 2.794% | 2.074% | 2.439% |  |  | 1.765% | 2.143% | 1.268% | 1.351% | 1.747% |  |  | 1.606% | 6.25% | 1.074% | 1.786% | 9.667% |  |  | 7.649% | 8.824% | 4.337% | 14.32% | 7.708% |  |  |  | 3.571% | 12.2% | 0.2294% | 1.099% |  |  |  |  | 6.087% | 6.032% | 6.25% |  |  | 8.217% | 4.425% | 3.915% | 2.121% | 1.961% | [7 empty] | 4.94% | 6.688% | 5.648% | 7.566% | 2.899% | 2.302% | 3.531% | 2.528% | 2.496% | 2.821% | 2.434% | 1.656% | 3.545% | 8.222% | 9.044% | 2.884% | 6.124% | 4.07% | 3.061% |  | 4.94% | 6.688% | 5.648% | 7.566% | 2.899% | 2.302% | 3.531% | 2.528% | 2.496% | 2.821% | 2.434% | 1.656% | 3.545% | 8.222% | 9.044% | 2.884% | 6.124% |  |  |  | 5.582% | 2.756% | 2.995% | 4.598% |  | 5.473% | 2.695% | 3.514% | 6.007%
| Final Defect Rate | 3.443% | 2.861% | 1.826% | 4.762% | 2.022% | 7.407% | 7.407% | 0.4525% | 2.052% | 2.597% | 3.605% | 0.8929% | 1.399% | 1.153% | 0.5525% | 1.639% | 0.463% | 1.004% | 0.8439% | 1.429% | 1.6% | 1.832% | 1.171% | 1.171% | 0.8811% | 0.6024% | 1.288% | 1.527% | 0.6309% | 1.976% | 1.932% | 2.878% |  |  |  |  | 0.9009% | 0.5891% |  |  | 0.289% | 0.2954% | 0.1447% | 0.8621% | 0% |  |  |  | 0.3021% | 2.077% | 1.603% | 0.4237% |  |  | 0.1447% | 0.4237% | 0.7353% | 0% | 0% |  |  | 0.7353% | 1.429% | 0.7042% | 0.9009% | 1.747% |  |  | 1.46% | 6.25% | 0.6135% | 1.786% | 9.667% |  |  | 4.104% | 5.294% | 4.337% | 2.105% | 5.68% |  |  |  | 3.571% | 12.2% | 0.2294% | 1.099% |  |  |  |  | 6.087% | 6.032% | 6.25% |  |  | 8.217% | 4.425% | 3.737% | 2.121% | 1.961% | [7 empty] | 3.443% | 3.571% | 3.028% | 1.143% | 1.065% | 1.151% | 1.585% | 0.7435% | 0.3192% | 1.099% | 0.2671% | 1.104% | 3.399% | 4.685% | 4.044% | 2.884% | 6.124% | 4.036% | 3.019% |  | 3.443% | 3.571% | 3.028% | 1.143% | 1.065% | 1.151% | 1.585% | 0.7435% | 0.3192% | 1.099% | 0.2671% | 1.104% | 3.399% | 4.685% | 4.044% | 2.884% | 6.124% |  |  |  | 2.239% | 0.9947% | 1.644% | 3.896% |  | 2.444% | 0.9575% | 1.926% | 4.397%
□ Tape Auto-Applicator Trouble Log
□ Daily Results | [108 empty] | □ 주별 Total | [19 empty] | □ 주별 평균 | [19 empty] | □ 월별 Total |  |  |  |  | □ 월별 평균
Category | [109 empty] | 1-1W | 1-2W | 1-3W | 1-4W | 1-5W | 2-1W | 2-2W | 2-3W | 2-4W | 3-1W | 3-2W | 3-3W | 3-4W | 3-5W | 4-1W | 4-2W | 4-3W | 4-4W | 4-5W |  | 1-1W | 1-2W | 1-3W | 1-4W | 1-5W | 2-1W | 2-2W | 2-3W | 2-4W | 3-1W | 3-2W | 3-3W | 3-4W | 3-5W | 4-1W | 4-2W | 4-3W | 4-4W | 4-5W |  | 1월 | 2월 | 3월 | 4월 |  | 1월 | 2월 | 3월 | 4월 | time axis 2026-01-02 to 2026-04-30
Day Shift |  | 95 | 27 | 85 | 89 | 59 | 58 | 66 | 101 | 63 | 67 | 31 | 87 | 58 | 18 | 33 | 25 | 48 | 31 | 40 | 45 | 20 | 22 | 50 | 42 | 36 | 51 | 52 | 50 | 52 | 26 | 39 | 52 |  |  |  |  | 26 | 66 | 64 |  | 55 | 74 | 69 | 71 | 75 | 0 |  |  | 25 | 92 | 51 | 56 |  |  | 33 | 48 | 38 | 38 | 52 | 48 |  | 58 | 43 | 63 | 57 | 0 |  |  | 39 | 47 | 66 | 77 | 77 |  |  | 22 | 29 | 25 | 118 | 123 |  |  | 48 | 77 | 86 | 90 | 83 | [5 empty] | 89 | 66 |  |  | 136 | 62 | 78 | 36 | 37 | [7 empty] | 95 | 318 | 328 | 221 | 184 | 201 | 271 | 156 | 344 | 224 | 257 | 221 | 306 | 51 | 266 | 384 | 155 | 349 | 213 |  | 95 | 63.6 | 65.6 | 44.2 | 36.8 | 40.2 | 45.1667 | 52 | 57.3333 | 56 | 42.8333 | 44.2 | 61.2 | 25.5 | 88.6667 | 76.8 |  |  |  |  | 1146 | 972 | 1059 | 1367 |  | 61.04 | 48.675 | 45.9467 | 82.7333
Night Shift |  | 93 | 80 | 70 | 89 | 59 | 73 | 65 | 78 | 72 | 59 | 63 | 69 | 36 | 81 | 46 | 62 | 82 | 34 | 53 | 47 | 34 | 54 | 43 | 37 | 37 | 32 | 48 | 41 | 38 | 61 | 32 | 36 |  |  |  |  | 56 | 60 | 0 |  | 70 | 106 | 54 | 78 | 28 | 0 |  |  | 36 | 37 | 37 | 38 |  |  | 41 | 37 | 33 | 58 | 53 |  |  | 110 | 32 | 35 | 51 | 30 |  |  | 51 | 10 | 66 | 62 | 71 |  |  | 38 | 49 | 37 | 67 | 24 |  |  | 21 | 12 | 111 | 0 | 128 |  |  |  |  | 103 | 69 | 110 |  |  | 114 | 97 | 92 | 54 | 64 | [7 empty] | 93 | 371 | 337 | 294 | 250 | 203 | 256 | 116 | 336 | 148 | 222 | 258 | 260 | 87 | 128 | 272 | 282 | 421 | 307 |  | 93 | 74.2 | 67.4 | 58.8 | 50 | 40.6 | 42.6667 | 38.6667 | 56 | 37 | 44.4 | 51.6 | 52 | 43.5 | 42.6667 | 54.4 |  |  |  |  | 1345 | 911 | 975 | 1410 |  | 68.68 | 44.4833 | 45.7 | 48.5333
Stoppage Count |  | 188 | 107 | 155 | 178 | 118 | 131 | 131 | 179 | 135 | 126 | 94 | 156 | 94 | 99 | 79 | 87 | 130 | 65 | 93 | 92 | 54 | 76 | 93 | 79 | 73 | 83 | 100 | 91 | 90 | 87 | 71 | 88 | 0 | 0 | 0 | 0 | 82 | 126 | 64 | 0 | 125 | 180 | 123 | 149 | 103 | 0 | 0 | 0 | 61 | 129 | 88 | 94 | 0 | 0 | 74 | 85 | 71 | 96 | 105 | 48 | 0 | 168 | 75 | 98 | 108 | 30 | 0 | 0 | 90 | 57 | 132 | 139 | 148 | 0 | 0 | 60 | 78 | 62 | 185 | 147 | 0 | 0 | 69 | 89 | 197 | 90 | 211 | 0 | 0 | 0 | 0 | 103 | 158 | 176 | 0 | 0 | 250 | 159 | 170 | 90 | 101 | 0 | 0 | 0 | 0 | 0 | 0 |  | 188 | 689 | 665 | 515 | 434 | 404 | 527 | 272 | 680 | 372 | 479 | 479 | 566 | 138 | 394 | 656 | 437 | 770 | 520 |  | 188 | 137.8 | 133 | 103 | 86.8 | 80.8 | 87.8333 | 90.6667 | 113.3333 | 93 | 87.2333 | 95.8 | 113.2 | 69 | 131.3333 | 131.2 | 0 | 0 | 0 |  | 2491 | 1883 | 2034 | 2777 |  | 129.72 | 93.1583 | 91.6467 | 131.2667
Day Shift |  | 50 | 20 | 50 | 50 | 50 | 60 | 30 | 70 | 30 | 30 | 20 | 40 | 30 | 10 | 20 | 20 | 30 | 20 | 20 | 20 | 10 | 10 | 30 | 20 | 20 | 30 | 30 | 30 | 30 | 10 | 20 | 30 |  |  |  |  | 20 | 30 | 30 |  | 30 | 40 | 40 | 40 | 40 | 0 |  |  | 20 | 50 | 30 | 30 |  |  | 20 | 20 | 30 | 20 | 30 | 53 |  | 30 | 20 | 25 | 36 | 0 |  |  | 20 | 20 | 57.5 | 51 | 32.5 |  |  | 31 | 25 | 12 | 60 | 73 |  |  | 37 | 48.5 | 57 | 45 | 43 | [5 empty] | 37 | 72 |  |  | 57 | 94 | 30 | 41 | 53 | [7 empty] | 50 | 230 | 180 | 120 | 100 | 110 | 150 | 80 | 190 | 130 | 173 | 111 | 181 | 56 | 145 | 230.5 | 109 | 275 | 218 |  | 50 | 46 | 36 | 24 | 20 | 22 | 25 | 26.6667 | 31.6667 | 32.5 | 28.8333 | 22.2 | 36.2 | 28 | 48.3333 | 46.1 |  |  |  |  | 680 | 530 | 651 | 977.5 |  | 35.2 | 26.3333 | 29.5467 | 47.2167
Night Shift |  | 50 | 40 | 40 | 50 | 30 | 50 | 30 | 50 | 40 | 30 | 30 | 40 | 20 | 50 | 30 | 50 | 40 | 20 | 30 | 20 | 20 | 30 | 20 | 20 | 20 | 20 | 30 | 20 | 20 | 30 | 20 | 20 |  |  |  |  | 30 | 30 | 0 |  | 40 | 50 | 30 | 40 | 10 | 0 |  |  | 20 | 20 | 20 | 20 |  |  | 20 | 20 | 20 | 30 | 30 |  |  | 50 | 20 | 20 | 19 | 55 |  |  | 30 | 5 | 76 | 23 | 40.5 |  |  | 35 | 27 | 10.5 | 20 | 15 |  |  | 22 | 28 | 50 | 132 | 25 |  |  |  |  | 89 | 36 | 54 |  |  | 56 | 47 | 47 | 28.5 | 44 | [7 empty] | 50 | 210 | 180 | 190 | 130 | 110 | 140 | 60 | 170 | 80 | 120 | 164 | 174.5 | 62 | 45.5 | 257 | 179 | 222.5 | 166.5 |  | 50 | 42 | 36 | 38 | 26 | 22 | 23.3333 | 20 | 28.3333 | 20 | 24 | 32.8 | 34.9 | 31 | 15.1667 | 51.4 |  |  |  |  | 760 | 480 | 600.5 | 870.5 |  | 38.4 | 23.4167 | 28.54 | 33.2833
Long-Duration Loss (min) |  | 0 | 360 | 60 | 0 | 0 | 0 | 100 | 0 | 170 | 0 | 0 | 90 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 110 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 50 | 0 |  |  | 300 | 40 | 0 | 0 |  |  | 0 | 0 | 0 | 30 | 80 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 80 | 0 | 0 | 0 | 0 |  |  | 0 | 130 | 215 | 5 | 145 |  |  | 0 | 50 | 60 | 0 | 0 | [5 empty] | 27 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 420 | 270 | 90 | 140 | 530 | 0 | 0 | 50 | 340 | 110 | 0 | 80 | 130 | 365 | 110 | 27 | 0 | 0 |  | 0 | 84 | 54 | 18 | 28 | 106 | 0 | 0 | 8.3333 | 85 | 22 | 0 | 16 | 65 | 121.6667 | 22 |  |  |  |  | 920 | 580 | 660 | 502 |  | 36.8 | 28.5833 | 37.6 | 71.8333
Total Lost Time (min) |  | 100 | 420 | 150 | 100 | 80 | 110 | 160 | 120 | 240 | 60 | 50 | 170 | 50 | 60 | 50 | 70 | 100 | 40 | 50 | 40 | 140 | 570 | 50 | 40 | 40 | 50 | 60 | 50 | 50 | 40 | 40 | 50 | 0 | 0 | 0 | 0 | 50 | 60 | 30 | 0 | 70 | 90 | 70 | 80 | 100 | 0 | 0 | 0 | 340 | 110 | 50 | 50 | 0 | 0 | 40 | 40 | 50 | 80 | 140 | 53 | 0 | 80 | 40 | 45 | 55 | 55 | 0 | 0 | 130 | 25 | 133.5 | 74 | 73 | 0 | 0 | 66 | 182 | 237.5 | 85 | 233 | 0 | 0 | 59 | 126.5 | 167 | 177 | 68 | 0 | 0 | 0 | 0 | 89 | 100 | 126 | 0 | 0 | 113 | 141 | 77 | 69.5 | 97 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100 | 860 | 630 | 400 | 370 | 750 | 290 | 140 | 410 | 550 | 403 | 275 | 435.5 | 248 | 555.5 | 597.5 | 315 | 497.5 | 384.5 |  | 100 | 172 | 126 | 80 | 74 | 150 | 48.3333 | 46.6667 | 68.3333 | 137.5 | 74.8333 | 55 | 87.1 | 124 | 185.1667 | 119.5 | 0 | 0 | 0 |  | 2360 | 1590 | 1911.5 | 2350 |  | 110.4 | 78.3333 | 95.6867 | 152.3333
Long-Duration Loss Details
Date | Loss Detail
2026-01-05 | Tape release liner Y-axis fixture broken; repair: 360 min
2026-01-06 | Silicone application robot Y-axis alarm; repair: 60 min | [128 empty] | 130 | 84 | -46 | -35.38%
2026-01-12 | Day shift: 2× unexplained full origin resets (40 min lost); tape dislodgement 1× (20 min lost); night shift: feed belt temp fix (40 min lost) | [128 empty] | 110 | 83 | -27 | -24.55%
2026-01-14 | Night shift: silicone release liner Y-axis error repair: 170 min lost
2026-01-19 | Automation equipment tape dislodgement defect repair: 90 min lost
2026-01-26 | Product vacuum suction failure repair: 30 min lost
2026-01-30 | Night shift: transfer device wire breakage stoppage: 110 min lost
2026-02-02 | Unloading chuck broken; chuck redesigned and program updated
2026-02-03 | No long-duration loss
2026-02-04 | No long-duration loss
2026-02-05 | No long-duration loss
2026-02-06 | No long-duration loss
2026-02-09 | No long-duration loss
2026-02-10 | No long-duration loss
2026-02-11 | No long-duration loss
2026-02-12 | No long-duration loss
2026-02-13 | No long-duration loss
2026-02-14 | No long-duration loss
2026-02-16 | Non-operating
2026-02-17 | Non-operating
2026-02-18 | Non-operating
2026-02-19 | No long-duration loss
2026-02-20 | No long-duration loss
2026-02-21 | No long-duration loss
2026-02-23 | No long-duration loss
2026-02-24 | No long-duration loss
2026-02-25 | No long-duration loss
2026-02-26 | No long-duration loss
2026-02-27 | Silicone center-axis drift – Chinese engineer remote program adjustment: 50 min lost
2026-02-28 | Non-operating
2026-03-01 | Non-operating
2026-03-02 | Non-operating
2026-03-03 | Silicone shot section Y/Z-axis failure repair: 300 min lost
2026-03-04 | Tape section suction miss repair: 40 min lost
2026-03-05 | No long-duration loss
2026-03-06 | No long-duration loss
2026-03-07 | Non-operating
2026-03-08 | Non-operating
2026-03-09 | No long-duration loss
2026-03-10 | No long-duration loss
2026-03-11 | No long-duration loss
2026-03-12 | Tape sub-material support bracket jam repair: 30 min lost
2026-03-13 | Silicone shot section Z-axis failure repair (50 min lost); tape section vacuum suction miss repair (30 min lost)
2026-03-14 | No long-duration loss
2026-03-15 | Non-operating
2026-03-16 | No long-duration loss
2026-03-17 | No long-duration loss
2026-03-18 | No long-duration loss
2026-03-19 | No long-duration loss
2026-03-20 | No long-duration loss
2026-03-21 | Non-operating
2026-03-22 | Non-operating
2026-03-23 | Tape section cylinder not actuating repair (30 min lost); silicone section jig X-axis not moving repair (50 min lost)
2026-03-24 | No long-duration loss
2026-03-25 | No long-duration loss
2026-03-26 | No long-duration loss
2026-03-27 | No long-duration loss
2026-03-28 | Non-operating
2026-03-29 | Non-operating
2026-03-30 | No long-duration loss
2026-03-31 | Tape dislodgement inspection/adjustment: 120 min lost; release agent removal error: 10 min lost
2026-04-01 | Release liner removal failure repair: 215 min
2026-04-02 | Transfer jig not actuating repair: 90 min
2026-04-03 | Tape right-side suction pad torn; repair: 145 min
2026-04-04 | Non-operating
2026-04-05 | Non-operating (manual tape work performed)
2026-04-06 | No long-duration loss
2026-04-07 | Robot suction failure repair: 50 min lost
2026-04-08 | Tape vacuum fault repair: 60 min lost
2026-04-09 | No long-duration loss
2026-04-10 | No long-duration loss
2026-04-11 | Non-operating
2026-04-12 | Non-operating
2026-04-20 | No long-duration loss
2026-04-21 | No long-duration loss
2026-04-22 | No long-duration loss
2026-04-23 | No long-duration loss
2026-04-24 | No long-duration loss
2026-04-25 | Non-operating (manual tape work performed)
2026-04-26 | Non-operating